## Slide 1: Winthrop – Revere Street Project
Construction Update
Public Information Meeting
April 12, 2025

## Slide 2
Agenda
Welcome and Introductions
  Project Team
Proposed Improvements
Construction Progress to Date
Construction Schedule
Work Hours
Traffic Impacts
Questions & Answers

## Slide 3
Project Team
Town of Winthrop
  Proponent of the Project
  Responsible for funding design, permitting, and right-of-way acquisition
MassDOT’s Highway Division
  Responsible for administering design process, funding construction, and providing Resident Engineer services
CHA Consulting, Inc.
  Responsible for design
A.R. Belli, Inc.
  Responsible for construction

## Slide 4
Project Area
Key Facts
0.6 mile length
16,000 vehicles per day
Contract Value: $7.5 million

## Slide 5
Project Improvements
Infrastructure Upgrades
  Pavement:
    Reconstruct existing pavement and sidewalks
  Traffic Signals:
    Replace all traffic signal equipment at Magee’s Corner and at Crest Avenue intersection.
  Drainage:
    Replace old clay drainage system with new concrete/ ductile iron pipes and new catch basins
    Regrade roadway to reduce flooding & ponding
  Lighting:
    Replace light poles with new decorative light poles
  Utilities:
    National Grid to replace old gas main

## Slide 6
Project Improvements (cont’d)
Pedestrians
  Reconstruct sidewalks and curb ramps for Americans with Disability Act (ADA) compliance
  Traffic signal equipment upgrades for pedestrian accessibility
  Add Rectangular Rapid Flashing Beacons (RRFB) at crosswalks
  New crosswalks:
    Across Shirley Street at intersection with Revere Street
    Across Revere Street at intersection with Locust Street
Bicycles
  Stripe 5’ wide bike lanes
    Northern side of road between Main Street and Shirley Street
      Maintain on-street parking on south side of road
    Both sides of road between Shirley Street and Crest Avenue
RRFB Example

## Slide 7
Project Improvements (cont’d)
Public Bus Transit
  Relocate bus stops based on coordination with the MBTA
    Generally, move bus stops to the far side at intersections for improved operations
  Widen sidewalks at bus stops
  Equip traffic signals with Transit Priority Relays to reduce bus delays at signals
Vehicles
  Reduce congestion at Kennedy Drive during school pick-up/ drop-off hours
    Widen roadway to provide “pull-off” area for vehicles queued on Revere Street

## Slide 8
Construction Progress to date
Underground work 95% complete
  Drainage system completely reconstructed
  Gas main replaced
  Conduit installed for new traffic signals
  Other minor utility relocations

## Slide 9
Construction Schedule
Spring – Summer – Fall '25
  Roadway, traffic signal and sidewalk reconstruction (Main to Kennedy)
  MORE DETAILED INFO NEEDED FOR 2025 CONSTRUCTION
Summer '26 – Fall '26
  Roadway, traffic signal and sidewalk reconstruction (Kennedy to Crest)

## Slide 10
Work Hours
Typical Work Shift
  Mondays through Fridays
  7:00 AM to 3:30 PM each day
  Work requiring lane closures shall not be carried out during peak traffic hours of 6:00 AM to 9:00 AM and 3:00 PM to 7:00 PM.
  No lane closures near Kennedy Drive during school pick-up/ drop-off hours

## Slide 11
Traffic Impacts
Maintain at least one lane of travel on Revere Street throughout construction. Two-way traffic will be maintained at all times using alternating flow.
Police details will be utilized to maintain safe travel for the public during construction
One lane of traffic will generally be impacted daily

## Slide 12
Points of Contact
Town of Winthrop Department of Public Works
  Director, Steven Calla
    617-846-1341
MassDOT
  Resident Engineer, Tibebu Gashaw
    tibebu.gashaw@dot.state.ma.us
Visit the Town website for biweekly updates of construction progress and upcoming work